## Sheet1
Lofthus frukt og saft |  |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Legend
|  |  | M | T | O | TH | F | SA | SU | M | T | O | TH | F | SA | SU | M | T | O | TH | F | SA | SU | M | T | O | TH | F | SA | SU | M | T | O | TH | F | SA | SU | Critical Path
Branding & Customer Collaboration | Time spent | 9h | [35 empty] | Uncompleted task
Website name | PO (Product Owner) |  | Week 1 M: 4 | Completed task/segment
Research Keywords | PO & Bjorn Researcher |  | Week 1 T: 5
Website content framework | PO & Alice Designer | bar: Week 1 T to Week 1 O
Style-Tile | PO & Alice Designer | bar: Week 1 TH to Week 1 F
Secure Assets | Time spent | 0h | bar: Week 2 M to Week 2 T
Buy Domain | PO | bar: Week 2 M
Research server options | PO | bar: Week 2 M
Rent Server | PO | bar: Week 2 T
Hire photographer | Alice Designer | bar: Week 2 M
Website Content & Design | Time spent | 5h
Acquire Content from Client | Bjorn Researcher | bar: Week 2 O
Find/Create missing Content | Bjorn Researcher + Photographer |  | Week 3 M: 5
Create website design selections & Templates | Alice Designer; Alex assisting | bar: Week 2 M to Week 2 F
Commit & sign-off Design & template | Alice Designer and PO Approver | bar: Week 2 F
Website Construction | Time spent | 10h
HTML - Setup & Insert Content | Time spent | 5h
Create framework based on website Template | Helena HTML | bar: Week 3 M
Insert placeholder content | Helena HTML | bar: Week 3 M
Create Contact us form in HTML | Helena HTML | bar: Week 3 M to Week 3 T
Setup Links | Helena HTML | bar: Week 3 T to Week 3 O
Collaborate, test and finalize - With CSS Team | HTML & CSS Team; PO Approver |  | Week 3 F: 5
Add Content | Helena HTML; Bjorn Assisting | bar: Week 3 F
CSS - Create website Template | Time spent | 5h
Create Framework based on website Template | Alex CSS; Alice Assisting | bar: Week 3 M
Design Global Header & Navigation | Alex CSS; Alice Assisting | bar: Week 3 M
Design Global Body | Alex CSS; Alice Assisting | bar: Week 3 M
Design Global Footer | Alex CSS; Alice Assisting | bar: Week 3 M
Home Page: Banner, Articles, Asides | Alex CSS; Alice Assisting | bar: Week 3 T to Week 3 O
Contact us page: Contact Form, Contact Information, Map | Alex CSS; Alice Assisting | bar: Week 3 O to Week 3 TH
Product Information Page: Articles: Product, Production | Alex CSS; Alice Assisting | bar: Week 3 TH to Week 3 F
About us Page: Articles: Vision, History, Leadership, Goals | Alex CSS; Alice Assisting | bar: Week 3 F to Week 3 SA
Collaborate, test and finalize - With HTML Team | CSS & HTML Team; PO Approver |  | Week 4 M: 5
Test, Finalize Commit and Sign-off | Time spent | 0h
Rigourous testing and debugging | HTML & CSS Team | bar: Week 4 O to Week 4 TH
Finalize and commit | PO Approver & Team | bar: Week 4 F
Teach company IT the Code | HTML & CSS Team | bar: Week 5 M to Week 5 T
Sign-Off website | PO Approver | bar: Week 5 O
| Total Time spent | 24h | 4 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0